## Sheet1
BUG ID |  |  |  | BUG OVERVIEW |  |  | ENVIRONMENT |  |  | BUG DETAILS |  |  | BUG TRACKING
ID | TITLE | REPORTED BY | DATE REPORTED | SUMMARY | URL | SCREENSHOT | PLATFORM | OPERATING SYSTEM | BROWSER | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | DATE OF FIX
D-01 | Unable to fetch all flight details using get method | Meenachi Rajasekar | 2023-01-12 | When the user requests to fetch all the existing flight details, getting 404 not found in response | http://localhost:8081/api/v1/flight | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new GET request 4. Select GET from dropdown 5. Send a request using given URL | 200 | 404 | Major | High
D-02 | Unable to create flight with ID -01 | Meenachi Rajasekar | 2023-01-12 | When the user send post request with payload without any existing flight in db, flight should be created with Flight Id - 1 instead of 2 | http://localhost:8081/api/v1/flight/save | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the Flight ID in response body | Flight ID -01 should be generated | Flight ID -02 is generated | Minor | Medium
D-03 | Blank passwords are accepted while registering new user | Meenachi Rajasekar | 2023-01-12 | When the user sends post request to register a new user with blank password, user shouldn’t be able to register. | http://localhost:8081/api/v1/user/register | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-04 | Invalid Mobile Numbers are accepted while registering as a new user | Meenachi Rajasekar | 2023-01-12 | When the user sends post request to register a new user with invalid mobile number, user shouldn’t be able to register. | http://localhost:8081/api/v1/user/register | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-05 | Empty Mobile Number Field is accepted while registering as a new user | Testing Team | 2023-01-12 | When the user sends post request to register a new user with Null Field in mobile number, user shouldn’t be able to register. | http://localhost:8081/api/v1/user/register | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-06 | Empty FirstName and LastName Fields are accepted while registering as a new user | Testing Team | 2023-01-12 | When the user sends post request to register a new user with Null Field in Firstname and Lastname fields, user shouldn’t be able to register. | http://localhost:8081/api/v1/user/register | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-07 | Same Flight Details with Different Flight ID | Testing Team | 2023-01-12 | When the user sends post request to create a new flight with same details, Flights with same Flight Info should not be created. | http://localhost:8081/api/v1/flight/save | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-08 | Same Flight Details with Null Flight ID | Testing Team | 2023-01-12 | When the user sends post request to create a new flight with Null value in Flight Id field, Flight with Empty Flight ID should not be created. | http://localhost:8081/api/v1/flight/save | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-09 | Flight with Same Origin and Destination | Testing Team | 2023-01-12 | When the user sends post request to create a new flight with Same Origin location and Destination Location, Flight should not be created. | http://localhost:8081/api/v1/flight/save | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-10 | Case sensitivity of Flight Number in Flight Creation | Testing Team | 2023-01-12 | When the user sends post request to create a new flight with Lowercases in Flight Number Field, Flight should not be created. | http://localhost:8081/api/v1/flight/save | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-11 | Flight with FlightDate earlier to present date | Testing Team | 2023-01-12 | When the user sends post request to create a new flight with FlightDate earlier to Present Date in Flight Date Field, Flight should not be created. | http://localhost:8081/api/v1/flight/save | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High
D-12 | Flight with Null Fare Field | Testing Team | 2023-01-12 | When the user sends post request to create a new flight with Null value in Fare Field, Flight should not be created. | http://localhost:8081/api/v1/flight/save | https://capgemini-my.sharepoint.com/:f:/p/meenachi_rajasekar/EmjL6Rzw-V5El677wS2VWlMBxJq5mA8FduWmd1HO0KjAPw?e=NOAyNP | HP | Windows 11 | Chrome - 108.0.5359.125 | 1. Start the application 2. Launch the postman tool 3. Create a new POST request with required payload 4. Send a request using given URL 5. Check the response and status code | 400 - Bad Request | 201- created | Major | High